## Slide 1
SPORTNEXUS
Development
Investment Proposal
Production-Ready · Sports Academy Booking Platform · iOS & Android
₹ 25,00,000
Total Investment · 6 Months Delivery · 7-Member Expert Team
Prepared: April 2026
Confidential · For Internal Use Only

## Slide 2
Executive Summary
SportNexus Platform at a Glance
💰
₹25,00,000
Total Investment
📅
6 Months
End-to-End Delivery
👥
7 Experts
Dedicated Team
🚀
3 Products
Mobile · API · Admin
Project Overview
• SportNexus is a production-grade sports academy booking platform enabling parents and students to discover, enroll, pay, and track training — all from a mobile app.
• Comprises a React Native mobile app (iOS + Android), a Fastify REST API with PostgreSQL/Redis/Socket.IO, and a Next.js admin dashboard — three integrated products.
• Core capabilities: GPS-based academy discovery, Razorpay online payments, live transport tracking, Firebase push notifications, admin analytics, and RBAC security.
• Built on PostgreSQL 16 with 12 data models, 22 indexes, Redis caching, BullMQ workers, HMAC webhook verification, and CI/CD pipelines — production-grade architecture.
• Total scope: 16 mobile screens, 28+ API endpoints, 7 admin pages, 12 DB tables, real-time Socket.IO, full DevOps setup, security audit, and 30-day post-launch support.

## Slide 3
Platform Components
Three integrated products delivered as one cohesive system
📱
Mobile Application
React Native 0.76 · Expo SDK 52
✓ 16 fully designed screens
✓ iOS & Android support
✓ Zustand state management
✓ React Query v5 data layer
✓ Socket.IO real-time sync
✓ Firebase push notifications
✓ QR code & payment receipts
✓ Offline-tolerant local store
⚙️
API Server
Fastify · Node.js · PostgreSQL 16
✓ 8 REST API route domains
✓ JWT auth + RBAC guards
✓ Razorpay payment gateway
✓ Socket.IO transit rooms
✓ BullMQ background workers
✓ Redis caching (5 & 10 min TTL)
✓ Zod input validation
✓ HMAC webhook verification
🖥️
Admin Dashboard
Next.js 14 · Tailwind CSS · Recharts
✓ 7 management pages
✓ Enrollment monitoring
✓ Revenue analytics charts
✓ Academy & slot management
✓ Daily transit operations
✓ Role-based access control
✓ Recharts data visualisations
✓ Vercel one-click deploy

## Slide 4
Core Features & Capabilities
Comprehensive feature set engineered for production use
🔍
Smart Academy Discovery
GPS-based search with sport, distance, rating, transport & fee filters. Redis-cached results.
📋
Multi-Step Enrollment Flow
Slot selection → duration → transport option → payment → booking confirmation with QR code.
💳
Online Payment Gateway
Razorpay integration — order creation, HMAC-SHA256 webhook verification, receipts & refunds.
🚌
Live Transport Tracking
Real-time driver location via Socket.IO. ETA, pickup stop order (TSP algorithm), status updates.
🔔
Push Notifications
Firebase Cloud Messaging. BullMQ scheduled alerts dispatched before slot time each morning.
⭐
Reviews & Ratings
Per-academy 1–5 star reviews. Aggregate rating recalculated on every new review submission.
📊
Admin Analytics
Revenue charts, enrollment trends, slot utilisation, daily transit ops — all in one dashboard.
🔐
Security & Auth
JWT + bcrypt refresh rotation, RBAC (5 roles), rate limiting, Zod validation, OWASP hardening.

## Slide 5
Technology Stack
Industry-standard, battle-tested technologies — no proprietary lock-in
Mobile
React Native 0.76 / Expo 52
TypeScript 5.x
Zustand (state mgmt)
TanStack Query v5
React Navigation v6
Expo Location + Notifs
React Native Maps
Socket.IO Client
Backend API
Node.js 20 + Fastify
TypeScript + Zod
PostgreSQL 16 (Prisma)
Redis 7 + BullMQ
Socket.IO (real-time)
Firebase Admin SDK
Razorpay SDK
JWT + bcrypt
Admin Panel
Next.js 14 App Router
Tailwind CSS v3
TypeScript
Recharts analytics
React Hook Form
Axios + SWR
shadcn/ui
Vercel deploy
Infrastructure
Docker Compose (dev)
Render.com (hosting)
PostgreSQL managed
Redis managed
Firebase Cloud Msg
Razorpay gateway
EAS Build (APK/IPA)
GitHub Actions CI/CD

## Slide 6
Development Scope
Complete deliverables included in this proposal
📱 Mobile App
Screens designed & built
16
Navigation stacks
3
Zustand state stores
3
Custom React hooks
4
Modal components
4
Platform targets
iOS + Android
⚙️ API Server
REST API domains
8
API endpoints
28+
Socket.IO events
5
BullMQ workers
2
Redis cache TTLs
5 min & 10 min
Rate limit rules
2 (global + auth)
🖥️ Admin + DB
Admin dashboard pages
7
Recharts dashboards
3
PostgreSQL tables
12
Database indexes
22
FK relationships
16
Enum domain types
5
🔧 DevOps + QA
Docker services
3 (API, PG, Redis)
CI/CD pipelines
2
EAS build profiles
3
Environment configs
3 (dev/preview/prod)
Security checks
OWASP Top 10
Test types
Unit + Integration

## Slide 7
Project Team Composition
Dedicated specialist team required for production-grade delivery
👨‍💻
Senior Full-Stack Developer
₹1,80,000/mo
Duration: 6 months
React Native + Fastify + PostgreSQL leadership
📱
Mobile Developer
₹1,50,000/mo
Duration: 5 months
Expo, React Native, animations, Socket.IO
🔧
Backend Developer
₹1,40,000/mo
Duration: 5 months
Fastify, PostgreSQL, Redis, BullMQ workers
🎨
UI/UX Designer
₹1,20,000/mo
Duration: 4 months
Figma, design system, all 16 screen flows
🔍
QA Engineer
₹90,000/mo
Duration: 3 months
Mobile + API testing, performance, security
☁️
DevOps Engineer
₹1,20,000/mo
Duration: 2 months
Docker, CI/CD, cloud infra, EAS builds
📊
Project Manager
₹1,10,000/mo
Duration: 6 months
Agile delivery, sprint planning, stakeholders

## Slide 8
Project Timeline
6-month phased delivery — from discovery to go-live
Phase 1
Discovery & Design
Wks 1–3
• Requirements workshop
• UI/UX wireframes
• DB schema design
• API contract spec
Phase 2
Core Development
Wks 4–12
• All 16 mobile screens
• API server + auth
• Admin dashboard
• DB setup & seed
Phase 3
Integrations
Wks 13–16
• Razorpay payments
• Firebase FCM
• Socket.IO transit
• Maps & geolocation
Phase 4
Testing & QA
Wks 17–20
• Unit & API tests
• Performance load test
• Security audit
• Bug-fix sprints
Phase 5
Deployment & Launch
Wks 21–22
• CI/CD pipelines
• Cloud deployment
• App store submit
• Go-live support
Phase 6
Handover & Support
Wks 23–24
• Documentation
• Code walkthrough
• 30-day warranty
• Knowledge transfer

## Slide 9
Detailed Cost Breakdown
Line-item pricing — effort hours × market rate
Deliverable / Component
Effort (hrs)
Rate (₹/hr)
Amount (₹)
Mobile App — 16 screens (React Native / Expo SDK 52)
400
₹1,500
₹ 6,00,000
API Server — 8 domains, Socket.IO, BullMQ workers
320
₹1,500
₹ 4,80,000
Admin Dashboard — Next.js 14, 7 pages, Recharts
160
₹1,500
₹ 2,40,000
UI/UX Design — all screens, design system, Figma
200
₹1,200
₹ 2,40,000
Database Design — 12 models, 22 indexes, seed data
80
₹1,500
₹ 1,20,000
QA & Testing — unit, integration, performance tests
160
₹1,000
₹ 1,60,000
DevOps & CI/CD — Docker, cloud deployment, pipelines
80
₹1,500
₹ 1,20,000
Project Management — agile planning, delivery tracking
120
₹1,200
₹ 1,44,000
Security Audit — OWASP Top 10, pen testing, hardening
60
₹1,500
₹ 90,000
Third-party Integrations — Razorpay, Firebase, Maps
80
₹1,500
₹ 1,20,000
Technical Documentation & Knowledge Transfer
60
₹1,000
₹ 60,000
Deployment, Go-Live Support & App Store Submission
40
₹1,500
₹ 60,000
Sub-total (Development)
₹ 24,34,000

## Slide 10
Total Investment Summary
All-inclusive pricing — no hidden costs
Cost Breakdown
Development & Engineering
₹24,34,000
Cloud Infrastructure & Hosting (1 yr)
₹ 60,000
App Stores, SSL & Domain (1 yr)
₹ 35,000
Buffer & Contingency Reserve (3%)
₹ 71,000
TOTAL INVESTMENT
₹ 25,00,000
What's Included
✅ 16-screen mobile app — iOS & Android
✅ Full API with 28+ endpoints & RBAC
✅ Admin dashboard with analytics
✅ Razorpay payment gateway (live)
✅ Real-time transport tracking (Socket.IO)
✅ Firebase push notification system
✅ OWASP security audit & hardening
✅ CI/CD pipelines + cloud deployment
✅ Complete source code & IP transfer
✅ 30-day post-launch warranty support

## Slide 11
Why This Investment Is Justified
Production-ready platform vs. a basic prototype
✗ Basic Prototype
₹6–8 Lakhs
✗ Single developer, 3 months
✗ No automated testing — bugs reach production
✗ Hardcoded data, no real database design
✗ Mock / demo payments only
✗ No real-time features (polling at best)
✗ Manual deployment, no CI/CD
✗ No security audit — OWASP vulnerabilities
✗ No documentation or knowledge transfer
✓ SportNexus — Production Ready
₹25 Lakhs
✓ 7-member specialist team, 6 months
✓ Unit + integration tests, load testing
✓ 12-table PostgreSQL schema, 22 indexes
✓ Live Razorpay with HMAC webhook verification
✓ Socket.IO real-time driver tracking
✓ CI/CD pipelines + cloud infra (Docker, Render)
✓ OWASP Top 10 audit, JWT + bcrypt security
✓ Full documentation + 30-day warranty support
💡 The ₹25L investment builds a platform you can launch commercially — not a demo. Real users, real transactions, real-time features, production infrastructure.

## Slide 12
SPORTNEXUS
Thank You
Ready to build the future of sports training in India.
₹25,00,000 · 6 Months · 7-Member Team · Production-Ready
₹25L
Investment
6 Mo
Delivery
3
Platforms
Questions? Let's align on the roadmap and get started.
Prepared: April 2026 · Confidential · For Internal Use Only